## Active
Action Plan
Background: doing business in China has become challenging due to political, demographic and structural challenges; trade tensions include high tariffs for China, Vietnam, Thailand, Indonesia. We have large strategic customers for paste wax brands in Asia Pacific and Middle East. | [5 empty] | Updated:
Focus: Philippines - strategic location, democratic, IP protection, business friendly, infrastructure, no duties between China / ASEAN countries, western thinking, US military presence, literacy, skilled labor force, language, culture, cost structure Target: starting point: establish a better site to manufacture paste wax brands; relocate Invisible Glass® Reach and Clean Tool production from China
2026-03-09
Team Members: |  | Brian, Pat, Matt G, Tyler, Leng, Matt B, Bob S, Belle, Dave D, HZ, Rob E
What-Deliverables |  |  |  | Who | By When-Target Date | Status
Philippines Market Entry
1 | site selection - building specification, floor space and height requirements, location, utilities, tenant improvements to base building?, mechanical/electrical trades availability?, sprinklered? Expansion pathway, weather/natural events? |  |  | Brian, Leng, Matt G., Matt B. | June 1 2026 | 25 | 100
[6 empty] | 50 | 75
2 | Entity formation |  |  | Rob E, Matt B. | March 23 2026 | 25 | 100
[6 empty] | 50 | 75
3 | Philippines government documents completion, PEZA docs including investment estimate |  |  | Matt B., Brian | April 1 2026 | 25 | 100
[6 empty] | 50 | 75
4 | local accounting, compliance partner(s) selection |  |  | Matt B., Leng, Rob E. | April 1 2026 | 25 | 100
[6 empty] | 50 | 75
5 | local banking partner selection |  |  | Rob E, Matt B., Leng | April 1 2026 | 25 | 100
[6 empty] | 50 | 75
6 | local Logistics partner(s) selection; Orient Primary, MIFFI Secondary |  |  | Brian, Tyler | March 1 2026 | 25 | 100
[6 empty] | 50 | 75
7 | Project Gantt chart |  |  | Brian, Leng, Matt B. | March 23 2026 | 25 | 100
[6 empty] | 50 | 75
8 | Stoner trademarks application & registration in the region |  |  | Harry | July 1 2026 | 25 | 100
[6 empty] | 50 | 75
9 | Is there an opportunity to sell Stoner brands in the Philippines? |  |  | Jon C, Gary, IMA?, Leng, Rob E | January 2027 | 25 | 100
[6 empty] | 50 | 75
Technology Transfer - Paste Wax Brands - Honey Wax®, Miracle Gloss®
10 | paste wax process design |  |  | Matt G | April 15 2026 | 25 | 100
[6 empty] | 50 | 75
11 | paste wax mfg and packaging equipment purchase, test in USA?, crate and ship to Philippines |  |  | Matt G, Matt B | May 1 2026 | 25 | 100
[6 empty] | 50 | 75
12 | paste wax equipment installation & start up in Philippines |  |  | Matt G | October 1 2026 | 25 | 100
[6 empty] | 50 | 75
13 | paste wax quality control procedures, process operating guide |  |  | Matt G, Tyler | July 1 2026 | 25 | 100
[6 empty] | 50 | 75
14 | paste wax packaging raw materials list and supplier(s) selection - cans and lids from China to start, outer carton from Philippines, pallets |  |  | Matt G, Brian, Leng | May 1 2026 | 25 | 100
[6 empty] | 50 | 75
15 | paste wax chemical raw materials list, and supplier(s) selection, NDA, substances list review |  |  | Matt G, Brian | May 1 2026 | 25 | 100
[6 empty] | 50 | 75
16 | (hour by hour) operations coordinator selection, two paste wax team members for 14,000 cans/week |  |  | Brian, Tyler, Matt G., Leng | July 1 2026 | 25 | 100
[6 empty] | 50 | 75
17 | replenishment cards and boards for paste wax brands raw materials, finished goods |  |  | Brian, Julie Anne, Tyler | September 1 2026 | 25 | 100
[6 empty] | 50 | 75
18 | Safety training for Team |  |  | Matt G, Tyler | October 1 2026 | 25 | 100
[6 empty] | 50 | 75
19 | P&L / pro forma - current state versus future state |  |  | Matt B, Brian, Leng | April 1 2026 | 25 | 100
[6 empty] | 50 | 75
Technology Transfer - Invisible Glass® Reach and Clean Tool
20 | IGRC Tool components from China/Thailand - assembly and packaging process design, quality control procedures, process operating guide |  |  | Pat, Tyler | July 1 2026 | 25 | 100
[6 empty] | 50 | 75
21 | IGRC Tool components from Philippines - printed card, outer carton, RFID tag?, other - pallets |  |  | Pat, Leng, Julie Anne | August 1 2026 | 25 | 100
[6 empty] | 50 | 75
22 | Confirm "product of the Philippines"; tariff (versus China) to USA; optimize product/HT code; valuation method; INCO term(s) |  |  | Tyler, Pat, Brian, Leng | May 1 2026 | 25 | 100
[6 empty] | 50 | 75
23 | IGRC Tool components - assembly and packaging - hour by hour staffing for 5,000 tools per week |  |  | Brian, Tyler, Pat, Leng | July 1 2026 | 25 | 100
[6 empty] | 50 | 75
24 | P&L / pro forma - China current state versus future state Phils |  |  | Pat, Matt B., Brian | April 1 2026 | 25 | 100
[6 empty] | 50 | 75
25 | Ship Stoner injection molding tooling from Thailand to Philippines - Complete |  |  | Pat, Leng, Brian | December 1 2025 | 25 | 100
[6 empty] | 50 | 75
26 | replenishment cards and boards for IGRCT raw materials, finished goods |  |  | Julie Anne, Tyler | July 1 2026 | 25 | 100
[6 empty] | 50 | 75
27 | IGRC Tool components - increased component manufacturing in Philippines, process design, partner(s) - easiest to hardest components list |  |  | Pat, Leng | June 1 2026 | 25 | 100
[6 empty] | 50 | 75
Potential Obstacles / Contingency Elements
| Tariffs - Philippines to USA |  | Geopolitical activities - USA

## Backlog
BACKLOG
Department |  |  |  | Updated | Updated:
Team Members
Deliverables |  | Who | Target Date |  | Status
1 | Create a "Check-In Checklist" process to mistake-proof process |  |  |  | 25 | 100
[5 empty] | 50 | 75
2 | Certificate of Analyses to F&S |  |  |  | 25 | 100
[5 empty] | 50 | 75
3 | Certificate of Conformance to Customer Standards to F&S |  |  |  | 25 | 100
[5 empty] | 50 | 75
4 | Shortest lead time via increased upstream visibility using SharePoint |  |  |  | 25 | 100
[5 empty] | 50 | 75
5 | Create Stock Black DLC |  |  |  | 25 | 100
[5 empty] | 50 | 75
6 | Second visit to Terry to learn |  | 2022-07-01 |  | 25 | 100
[5 empty] | 50 | 75
7 |  |  |  |  | 25 | 100
[5 empty] | 50 | 75
8 |  |  |  |  | 25 | 100
[5 empty] | 50 | 75
9 |  |  |  |  | 25 | 100
[5 empty] | 50 | 75
10 |  |  |  |  | 25 | 100
[5 empty] | 50 | 75
11 |  |  |  |  | 25 | 100
[5 empty] | 50 | 75
12 |  |  |  |  | 25 | 100
[5 empty] | 50 | 75
13 |  |  |  |  | 25 | 100
[5 empty] | 50 | 75
14 |  |  |  |  | 25 | 100
[5 empty] | 50 | 75
15 |  |  |  |  | 25 | 100
[5 empty] | 50 | 75
Potential Barriers/Contingency Elements

## Complete
COMPLETE
Department |  |  |  | Updated | Updated:
Team Members
Deliverables |  | Who | Complete Date |  | Status
1 | Benchmark visit with Terry in December 2019 |  |  |  | 25 | 100
[5 empty] | 50 | 75
2 | Electronic logs of all process operations |  |  |  | 25 | 100
[5 empty] | 50 | 75
3 | Physical logs of all process operations |  |  |  | 25 | 100
[5 empty] | 50 | 75
4 | Two types of coupons for material and physical analyses |  |  |  | 25 | 100
[5 empty] | 50 | 75
5 | Short lead time |  |  |  | 25 | 100
[5 empty] | 50 | 75
6 | 30% discounted pricing |  |  |  | 25 | 100
[5 empty] | 50 | 75
7 | Establish similar pricing structure to what F&S currently receiving |  |  |  | 25 | 100
[5 empty] | 50 | 75
8 | Final Inspection Process |  |  |  | 25 | 100
[5 empty] | 50 | 75
9 |  |  |  |  | 25 | 100
[5 empty] | 50 | 75
10 |  |  |  |  | 25 | 100
[5 empty] | 50 | 75
11 |  |  |  |  | 25 | 100
[5 empty] | 50 | 75
12 |  |  |  |  | 25 | 100
[5 empty] | 50 | 75
13 |  |  |  |  | 25 | 100
[5 empty] | 50 | 75
14 |  |  |  |  | 25 | 100
[5 empty] | 50 | 75
15 |  |  |  |  | 25 | 100
[5 empty] | 50 | 75
Potential Barriers/Contingency Elements
8 | create 5 year projection -- informs behavior today -- money guide pro? Other? | Tripp, Steve | 2021-07-01 |  | 25 | 100
[5 empty] | 50 | 75